## Tasks
Task ID | Task Name | Bucket Name | Progress | Priority | Assigned To | Created By | Created Date | Start date | Due date | Is Recurring | Late | Completed Date | Completed By | Completed Checklist Items | Checklist Items | Labels | Description
9bkfyJC3ZEGaekBCJraRwskAAiX7 | Merge UI Into one app | Completed | Completed | Medium | Madanayake P.C.S. it21181788;Harshana W.C. it21175466;Hettiarachchi H.K.Y.K. it21181474;Mendis T.S.P it21207136 | Harshana W.C. it21175466 | 11/30/2024 |  | 01/28/2025 | false | false | 03/16/2025 | Harshana W.C. it21175466
b-MwZDfJO0aYOczNW8ZcwMkABkXd | Make child friendly UI (Puzzle) | To-Do | Completed | Medium | Harshana W.C. it21175466 | Harshana W.C. it21175466 | 12/05/2024 |  | 02/10/2025 | false | false | 03/16/2025 | Harshana W.C. it21175466
AmiL9j7-00eWspT_Is9NK8kACjPa | Implement Level 2 of puzzle function | Completed | Completed | Medium | Harshana W.C. it21175466 | Harshana W.C. it21175466 | 12/05/2024 |  | 01/30/2025 | false | false | 2025-01-28 | Harshana W.C. it21175466 | 0/2 | Split image non-similar-size pieces.(instead of 2 x2, 4 x4);Improve python algorithm get difficulties according to each level and each child.
Y5kgxYUONUGdCCEaBYrmKMkAOQdV | Save difficulty and continue puzzle | Completed | Completed | Medium | Harshana W.C. it21175466 | Harshana W.C. it21175466 | 12/05/2024 |  | 01/31/2025 | false | false | 03/14/2025 | Harshana W.C. it21175466
xTkwkFDPZkmc4bJijPr9zMkANBdB | Capture Image Using Camara Function | Completed | Completed | Medium | Harshana W.C. it21175466 | Harshana W.C. it21175466 | 12/05/2024 |  | 11/20/2024 | false | false | 03/14/2025 | Harshana W.C. it21175466
S9NwegjDSkGBbRlJv5kr6skAKT15 | Backend algorithm Development (Puzzle Function) | Completed | Completed | Medium | Harshana W.C. it21175466 | Harshana W.C. it21175466 | 11/30/2024 |  | 02/20/2025 | false | false | 03/14/2025 | Harshana W.C. it21175466 |  |  | Red
tys2oWrSOUS-40GOoLzWvskAObPG | Generate child friendly images to puzzle. | To-Do | Completed | Medium | Harshana W.C. it21175466 | Harshana W.C. it21175466 | 12/05/2024 |  | 02/06/2025 | false | false | 03/14/2025 | Harshana W.C. it21175466
3KfWJGU7SkGCp0uTpm1B3skAIRkp | Research Paper Finalizing | To-Do | Completed | Medium | Madanayake P.C.S. it21181788;Harshana W.C. it21175466;Hettiarachchi H.K.Y.K. it21181474;Mendis T.S.P it21207136 | Harshana W.C. it21175466 | 03/14/2025 |  | 03/06/2025 | false | false | 03/14/2025 | Harshana W.C. it21175466
aQ6GX2gGbku-l56iYu1w4ckAAELY | Research Paper Writing | To-Do | Completed | Medium | Madanayake P.C.S. it21181788;Harshana W.C. it21175466;Hettiarachchi H.K.Y.K. it21181474;Mendis T.S.P it21207136 | Harshana W.C. it21175466 | 03/14/2025 |  | 03/04/2025 | false | false | 03/14/2025 | Harshana W.C. it21175466
RZyfrixWukinRB5Os_fAeMkAGEQX | Add Sound Clips | To-Do | Completed | Medium | Harshana W.C. it21175466 | Harshana W.C. it21175466 | 02/08/2025 |  |  | false | false | 03/14/2025 | Harshana W.C. it21175466
hUTKJpX8s0K6UqUX3AsadckAMRYU | UI Development | Doing | Completed | Medium | Harshana W.C. it21175466 | Harshana W.C. it21175466 | 02/08/2025 |  | 02/15/2025 | false | false | 02/08/2025 | Harshana W.C. it21175466
LLuY9pZzCEKCOrhPudkcDskANJ6l | Child friendly UI Design Figma | Doing | Completed | Medium | Harshana W.C. it21175466 | Harshana W.C. it21175466 | 12/27/2024 |  | 01/27/2025 | false | false | 01/24/2025 | Harshana W.C. it21175466
uCaFU7SwIkSFHUMD3ulUNckAAlWX | Puzzle demonstration Function | Completed | Completed | Medium | Harshana W.C. it21175466 | Harshana W.C. it21175466 | 12/05/2024 |  | 01/28/2025 | false | false | 01/24/2025 | Harshana W.C. it21175466 |  |  |  | Demonstrate the function to children how to drag and drop and entire process at initially.
1cqrx62pCkiV76rX6GvcrckAGJMv | Create Pattern Matching Function Basic UI | Completed | Completed | Medium | Harshana W.C. it21175466 | Harshana W.C. it21175466 | 11/30/2024 |  | 08/11/2024 | false | false | 01/23/2025 | Harshana W.C. it21175466
4BthBuwc00u6o5_z0KqsMckAIv_f | Create proposal report | Completed | Completed | Urgent | Madanayake P.C.S. it21181788;Harshana W.C. it21175466;Hettiarachchi H.K.Y.K. it21181474;Mendis T.S.P it21207136 | Harshana W.C. it21175466 | 11/30/2024 |  | 08/16/2024 | false | false | 01/05/2025 | Hettiarachchi H.K.Y.K. it21181474 |  |  | Green
WybPVKzcRUK_pcK8rWRHrMkADvZL | Add feature to view last time game activities(vocabulary) | Doing | Completed | Medium | Hettiarachchi H.K.Y.K. it21181474 | Hettiarachchi H.K.Y.K. it21181474 | 01/29/2025 |  | 02/01/2025 | false | false | 03/16/2025 | Harshana W.C. it21175466
82yxy8RbFEqHVZaOl_-zrckAMWar | Set Device Capabilities for Speech-to-text model (Vocabulary Function) | Testing | Completed | Medium | Hettiarachchi H.K.Y.K. it21181474 | Hettiarachchi H.K.Y.K. it21181474 | 12/07/2024 |  | 01/18/2025 | false | false | 03/16/2025 | Harshana W.C. it21175466
6kwyS1ZvjEmxbQbUl9gmJMkAH6O4 | Model Training for Hand Writing (Vocabulary Function) | Testing | Completed | Medium | Hettiarachchi H.K.Y.K. it21181474 | Hettiarachchi H.K.Y.K. it21181474 | 12/07/2024 |  | 01/25/2025 | false | false | 03/16/2025 | Harshana W.C. it21175466
cng5mKy61EeYhB1R0uXd-MkAK0Vm | generate Images according to questions | Completed | Completed | Medium | Mendis T.S.P it21207136 | Mendis T.S.P it21207136 | 12/05/2024 |  | 11/19/2024 | false | false | 03/16/2025 | Harshana W.C. it21175466
qfqododFuUKcT_NM3Ii0QckAMuzD | Make function undersandable to every one | To-Do | Completed | Medium | Madanayake P.C.S. it21181788 | Madanayake P.C.S. it21181788 | 12/05/2024 |  | 12/15/2024 | false | false | 03/16/2025 | Harshana W.C. it21175466
9xFz1mXr5Ue_SL0EusZi6skAMc1N | Create Spacial Skill Function Basic UI | Completed | Completed | Medium | Madanayake P.C.S. it21181788 | Harshana W.C. it21175466 | 11/30/2024 |  | 08/11/2024 | false | false | 03/16/2025 | Harshana W.C. it21175466
rruh_f6ykE6fSBa_7epoCMkAPtRM | Create questions for Vocabulary Function | Completed | Completed | Medium | Hettiarachchi H.K.Y.K. it21181474 | Hettiarachchi H.K.Y.K. it21181474 | 11/30/2024 |  | 10/03/2024 | false | false | 03/16/2025 | Harshana W.C. it21175466
O28POW8cCU-Nux-1fVJy5skAGaar | test upload images | Testing | Completed | Medium | Mendis T.S.P it21207136 | Mendis T.S.P it21207136 | 03/16/2025 |  | 03/11/2025 | false | false | 03/16/2025 | Mendis T.S.P it21207136
SU68j7z-sUejOlLBAx5DBskAOcFO | upload congratulation audio | To-Do | Completed | Medium | Mendis T.S.P it21207136 | Mendis T.S.P it21207136 | 03/16/2025 |  | 03/06/2025 | false | false | 03/16/2025 | Mendis T.S.P it21207136
1S6zrMzRsUCNN6Qz9oYjkskAMoEz | implement user improvement | To-Do | Completed | Medium | Mendis T.S.P it21207136 | Mendis T.S.P it21207136 | 03/16/2025 |  | 03/01/2025 | false | false | 03/16/2025 | Mendis T.S.P it21207136
eVH8gJr3C06tczJrcc3Tc8kAJkDl | Test the all levels in generate image | Testing | Completed | Medium | Mendis T.S.P it21207136 | Mendis T.S.P it21207136 | 01/24/2025 |  | 02/01/2025 | false | false | 03/16/2025 | Mendis T.S.P it21207136
DGQt7qi2REqlGhHqpV0n9ckAAOlY | generate progress report | To-Do | Completed | Medium | Madanayake P.C.S. it21181788;Mendis T.S.P it21207136 | Mendis T.S.P it21207136 | 12/05/2024 |  | 01/31/2025 | false | false | 03/16/2025 | Mendis T.S.P it21207136
nB7QyKbSsk2gB2tP_pBGq8kAAqfQ | Create play instructions video | To-Do | Completed | Medium | Mendis T.S.P it21207136 | Mendis T.S.P it21207136 | 01/24/2025 |  | 01/30/2025 | false | false | 03/16/2025 | Mendis T.S.P it21207136
buj17hLGgE-tq5j8Bg8OE8kAG0rF | Create 3 levels in vocabulary assessment | Completed | Completed | Medium | Hettiarachchi H.K.Y.K. it21181474 | Hettiarachchi H.K.Y.K. it21181474 | 12/07/2024 |  | 11/27/2024 | false | false | 01/29/2025 | Hettiarachchi H.K.Y.K. it21181474
DrXhKLnH9Ua6ydPV7uI9tckAMA0X | design user friendly UI for vocabulary function | Completed | Completed | Medium | Hettiarachchi H.K.Y.K. it21181474 | Hettiarachchi H.K.Y.K. it21181474 | 01/05/2025 |  | 01/31/2025 | false | false | 01/29/2025 | Hettiarachchi H.K.Y.K. it21181474
l63BV_CLtUyT2FugNPkpEckAPDIB | All level generates different images | Testing | Completed | Medium | Mendis T.S.P it21207136 | Mendis T.S.P it21207136 | 12/05/2024 |  |  | false | false | 01/28/2025 | Mendis T.S.P it21207136
1E1bn9E9t0Cxec3eP6fT4ckAHCJt | design user friendly UI | To-Do | Completed | Medium | Madanayake P.C.S. it21181788;Mendis T.S.P it21207136 | Mendis T.S.P it21207136 | 12/05/2024 |  | 01/26/2025 | false | false | 01/28/2025 | Mendis T.S.P it21207136 |  |  | Red
5XmS9Qenvk6_C9mgLNZMEskAF60c | design Intial UI | Completed | Completed | Medium | Mendis T.S.P it21207136 | Mendis T.S.P it21207136 | 12/05/2024 |  | 08/16/2024 | false | false | 01/24/2025 | Mendis T.S.P it21207136
b0XY8gnAl0yCeHd2k3iXW8kAK6wt | create 7 level in prepositions | Completed | Completed | Medium | Mendis T.S.P it21207136 | Mendis T.S.P it21207136 | 12/05/2024 |  | 10/22/2024 | false | false | 01/24/2025 | Mendis T.S.P it21207136
p08oUSC_5UmFmqpkcAtVJMkAMP_S | Create Relationship Matching Function Basic UI | Completed | Completed | Medium | Mendis T.S.P it21207136 | Harshana W.C. it21175466 | 11/30/2024 |  | 08/11/2024 | false | false | 01/24/2025 | Mendis T.S.P it21207136
41Dsd17KJEqJ0kZ3Ols6VskALwX7 | following model training environment | Doing | Completed | Medium | Mendis T.S.P it21207136 | Mendis T.S.P it21207136 | 12/05/2024 |  |  | false | false | 01/24/2025 | Mendis T.S.P it21207136
GJOpuBoNW0SwkTfPq1MI08kADouJ | Model training for difficulty level | To-Do | Completed | Medium | Madanayake P.C.S. it21181788;Mendis T.S.P it21207136 | Mendis T.S.P it21207136 | 12/05/2024 |  | 12/19/2024 | false | false | 01/24/2025 | Mendis T.S.P it21207136
U0vWsaO9rUyah2f7F54bTckAGgen | upload real world image option | To-Do | Completed | Medium | Mendis T.S.P it21207136 | Mendis T.S.P it21207136 | 12/05/2024 |  | 12/17/2024 | false | false | 01/24/2025 | Mendis T.S.P it21207136 |  |  | Red
6rmTcW7Sj0a8wkP7SadDKskAJVOX | Collect real data set | Doing | Completed | Medium | Mendis T.S.P it21207136 | Mendis T.S.P it21207136 | 12/05/2024 |  |  | false | false | 01/24/2025 | Mendis T.S.P it21207136
WveWYUUh2kio2_yFQSLLjckAJfY0 | Shuffle questions and add more questions (Vocabulary Function) | Completed | Completed | Medium | Hettiarachchi H.K.Y.K. it21181474 | Hettiarachchi H.K.Y.K. it21181474 | 12/07/2024 | 12/02/2024 | 12/28/2024 | false | false | 01/05/2025 | Hettiarachchi H.K.Y.K. it21181474
l913VV_FfkeBhcDwaDpVz8kAIxxs | Create Vocabulary Function Basic UI | Completed | Completed | Medium | Hettiarachchi H.K.Y.K. it21181474 | Harshana W.C. it21175466 | 11/30/2024 |  | 08/11/2024 | false | false | 01/05/2025 | Hettiarachchi H.K.Y.K. it21181474
G2zWUBs5nUaYc3zS8lUH58kAGtGl | Identify data requirements for AI/ML models | Testing | Completed | Medium | Hettiarachchi H.K.Y.K. it21181474 | Harshana W.C. it21175466 | 11/30/2024 |  | 11/01/2024 | false | false | 12/07/2024 | Hettiarachchi H.K.Y.K. it21181474
_Ccq82DL0k--4EMVGusvQ8kAAkCH | study about models for rainforcement learning | Doing | Completed | Medium |  | Madanayake P.C.S. it21181788 | 12/05/2024 |  |  | false | false | 12/06/2024 | Madanayake P.C.S. it21181788
Zg3pa0-9_Ua_imf6OU8wd8kAMviX | different item | No Bucket | Completed | Medium | Madanayake P.C.S. it21181788 | Madanayake P.C.S. it21181788 | 12/05/2024 |  | 12/06/2024 | false | false | 12/05/2024 | Madanayake P.C.S. it21181788
_4Yj2elxK06Jx_olUIVql8kAH6kV | Fix Image Loading Time | To-Do | Completed | Medium | Harshana W.C. it21175466 | Harshana W.C. it21175466 | 03/16/2025 |  | 03/14/2025 | false | false | 03/16/2025 | Harshana W.C. it21175466
Bbq4bp-qVE6w-sCif8st8MkAOApR | Fix UI Overflow Issues | To-Do | Completed | Medium | Harshana W.C. it21175466 | Harshana W.C. it21175466 | 03/16/2025 |  | 03/14/2025 | false | false | 03/16/2025 | Harshana W.C. it21175466
8lvuHo_UP0yaTfp-TLw9H8kAFL8_ | Generate Report | To-Do | Completed | Medium | Harshana W.C. it21175466 | Harshana W.C. it21175466 | 03/16/2025 |  | 03/06/2025 | false | false | 03/16/2025 | Harshana W.C. it21175466
dCXLNzdvnkmFhXhNBG8Te8kAK8-U | UI Testing | Testing | Completed | Medium | Harshana W.C. it21175466 | Harshana W.C. it21175466 | 03/16/2025 |  | 03/15/2025 | false | false | 03/16/2025 | Harshana W.C. it21175466
_xkbx_RolUCXGgGcQ2KGRMkADMEp | Add Sound Clips to UI | Doing | Completed | Medium | Harshana W.C. it21175466 | Harshana W.C. it21175466 | 03/16/2025 |  | 03/08/2025 | false | false | 03/16/2025 | Harshana W.C. it21175466

## Plan name
Plan name | Magic Mind Mobile App
Plan ID | OjppqMTqdUeSvnnIp-9W48kAAXKq
Date of export | 03/16/2025